## report
Responsible person | Name | Status | Priority | Created on | Start date | Completed on | Deadline
Mahesh | POJO classes | Completed | Yes | 2017-10-24 | 2017-10-24 | 2017-10-25 | 2017-10-25
Mahesh | Database Connection | Completed | Yes | 2017-10-25 | 2017-10-25 | 2017-10-26 | 2017-10-26
Karan | POJO classes | Completed | Yes | 2017-10-24 |  | 2017-10-26 | 2017-10-25
Mitalee | POJO classes | Completed | Yes | 2017-10-24 |  | 2017-10-26 | 2017-10-25
Karan | DAO Classes | Completed | Yes | 2017-10-24 |  | 2017-10-26 | 2017-10-25
Mitalee | DAO Classes | Completed | Yes | 2017-10-24 |  | 2017-10-26 | 2017-10-25
Mahesh | DAO Classes | Completed | Yes | 2017-10-24 | 2017-10-24 | 2017-10-27 | 2017-10-26
Mahesh | Commuter service | Completed | No | 2017-10-27 | 2017-10-27 | 2017-10-30 | 2017-10-27
Mahesh | Admin Service | Completed | No | 2017-10-27 | 2017-10-27 | 2017-10-30 | 2017-10-27
Karan | Commuter service | Completed | No | 2017-10-27 |  | 2017-10-30 | 2017-10-27
Mitalee | Admin Service | Completed | No | 2017-10-27 |  | 2017-10-30 | 2017-10-27
Karan | Admin Service | Completed | No | 2017-10-27 |  | 2017-10-30 | 2017-10-27
Mitalee | Commuter service | Completed | No | 2017-10-27 |  | 2017-10-30 | 2017-10-27
Mahesh | Use case | Completed | No | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24
Mahesh | User Stories | Completed | No | 2017-10-24 | 2017-10-24 | 2017-10-24
Mitalee | Use case | Completed | No | 2017-10-24 |  | 2017-10-24
Mitalee | User Stories | Completed | No | 2017-10-24 |  | 2017-10-24
Karan | User Stories | Completed | No | 2017-10-24 |  | 2017-10-24
Karan | Use case | Completed | No | 2017-10-24 |  | 2017-10-24
Karan | Class Diagram | Completed | No | 2017-10-24 |  | 2017-10-24